## Opportunity Worksheet
Opportunity Resolution Worksheet
Instructions: After completing your Safety Culture Assessment and reading your Final Report, you can use this worksheet to organize and prioritize your Opportunities for Improvement. Three examples are inserted below and the 10 Core Elements on the next sheet for your reference.
Opportunity | Associated Core Element(s) | Date Initiated | Champion | Resolution Team | Current State | Ideal State | Time Needed for completion | Resources Needed | Progress Update | Completion Date | Post Resolution Evaluation
Job Safety Briefings: Consistently using the railroad’s job safety briefing procedure with all identified elements as outlined in the safety rules could ensure all associated risks,including existing and potential hazards, are discussed. |  | 2024-01-15 | Safety Manager | Trainmaster Mechanical Roadmaster Safety Committee | No standardized briefing template to be used by all leaders across all crafts. | Briefing template that covers all primary safety topics consistantly with workgroup and situational customization for crafts, tasks, work location, etc. | 30 days | Time to meet and draft/edit/test and finalize a working template. | 1/20/24: First meeting to establish working template. 1/25/24: Template used in shift briefings with request for feedback from employees. Employees suggested adding weather, and rule of the week to briefing template. 2/1/24: Suggestions included into template. Updated template used, no new employee feedback. Workgroups like the new format. 2/10/24: Template approved and added to company safety action plan. | 2024-02-10 | Safety manager sampled numerous briefings 30 days post completion and observes improvement of consistancy and thoroughness among all departments and all shift start safety briefings.
Safety Committee: The railroad could reiterate to all employees the structure and function of the Safety Committee, as well as developing and posting meeting minutes at all on-duty locations. Greater awareness of the committee’s activities and accomplishments could increase employee understanding of and participation in the railroad’s commitment to continuous improvement. |  | 2024-01-15 | Safety Manager | Department heads | Inadequate understanding of safety committee and its activities and accomplishments. | A communication system implemented to highlight the work, activities, and accomplishments of the safety committee to all employees. | 30 days | Staff meeting to set the mechanism. Feedback from safety committee members and general employees. | 1/30/24: Staff meeting held to review current safety committee charter document and problem-solve for strategies to communicate system-wide. Solutions include adding a space on safety bulletin boards for meeting minutes. Safety manager will maintain a safety issue resolution cocument that communicates issues, actions, and resolutions to be posted next to minutes. Supervisors will be instructed to include updates at briefings and allow committe members to update workgroups periodically. 2/10/24: Meeting minutes and issue resolution template documents created, reviewed, and approved. Templates and safety committee communications processes added to company safety action plan. | 2024-02-10 | Safety manager frequently asked employees and safety committee members over the past 60 days and has received positive feedback that indicates employees are receiving information about safety committee activities and accomplishments much more readily than before this opportunity resolution effort.
Tracking Process: A list of health and safety reports could be generated that summarizes and tracks incidents and improves trending analysis. Furthermore, this summary could improve the communication of the reported issues and resolutions in a way that is easily reviewed by employees. |  | 2024-01-15 | Safety Manager | Department heads | Safety incident tracking and communication not communicated to employees. | A communication system implemented to communicate incidents, issues, and resolutions relating to safety that will inform employees about trends, risks, and resolutions. | 30 days | Staff meeting to set the mechanism. Feedback from safety committee members and general employees. | 1/30/24: Included in the effort above, a near-miss, incidents, and lessons-learned document will be included with communications coming out of the safety committee and posted as part of the minutes and issue resolution document above in a separate section of each document. This will be included in the February SAP document review. 2/10/24: Language from this issue resolution added to company safety action plan. | 2024-02-10 | Supervisors auditing bulletin boards for compliance.

## Ten Core Elements
STRONG SAFETY CULTURE
The Short Line Safety Institute has adopted the U.S. Department of Transportation Safety Council’s definition of a Strong Safety Culture. A Strong Safety Culture is defined as, “The shared values, actions, and behaviors that demonstrate a commitment to safety over competing goals and demands.”
TEN CORE ELEMENTS OF A STRONG SAFETY CULTURE
1. Leadership Is Clearly Committed to Safety
The importance of leadership in fostering a strong safety culture is indicated by the fact that almost all safety culture models explicitly mention leadership commitment to safety. Leaders across all layers of a railroad must model safety-first attitudes and behaviors. Employees learn what the accepted practices are in a railroad by following the examples set by its leaders.
2. The Railroad Practices Continuous Learning
Maintaining a strong safety culture necessitates a learning environment where opportunities to improve safety are continuously sought out and implemented. Railroads must be open to learning from accidents when they do happen and willing to make changes to prevent incidents in the future.
3. Decisions Demonstrate that Safety Is Prioritized Over Competing Demands
One of the most unique elements of an organization with a strong safety culture is that their decision-making processes clearly demonstrate that safety is prioritized over competing demands. Railroads with a strong safety culture will consistently choose safety over performance when faced with the choice of cutting corners to increase performance.
4. Reporting Systems and Accountability Are Clearly Defined
Organizations must ensure that reporting systems and lines of accountability are in place so that safety issues can be promptly identified, fully evaluated, and promptly addressed and corrected commensurate with their significance.
5. There Is a Safety Conscious Work Environment
Maintaining a strong safety culture also requires constant vigilance and an elevated awareness of the importance of safety. Employees should be encouraged to raise safety concerns and provided opportunities to raise concerns through reporting systems and procedures.
6. Employees Feel Personally Responsible for Safety
Employees who feel personally responsible for safety take more ownership in following safety procedures and are also more likely to speak up when they see other employees behaving in an unsafe manner. Personal responsibility empowers employees and helps the entire organization identify and correct risks proactively.
7. There Is Open and Effective Communication Across the Railroad
Employees must feel comfortable communicating to their supervisors about safety issues and communicating with their peers when they see unsafe behaviors. If the railroad is not communicating the importance of safety and encouraging their employees to speak up about safety, then safety risks are more likely to develop and less likely to be addressed before an accident occurs.
8. Mutual Trust Is Fostered between Employees and the Railroad
One of the cornerstones of any positive organizational culture is trust. Trust among all railroad employees, from craft employees to senior leaders, can go a long way to support safety by facilitating open and honest communication and minimizing fears of reprisal. Employees who have developed a relationship of trust with their supervisors may feel more willing to raise safety concerns in novel situations when they are unsure of how the railroad might respond.
9. The Railroad Is Fair and Consistent in Responding to Safety Concerns
Above and beyond having effective reporting procedures and processes in place, the railroad mustrespond to safety concerns in a manner that employees perceive as fair, just, and consistent. Employees should feel free to raise safety concerns without fear of retaliation.
10. Training and Resources Are Available to Support Safety
Those who manage and operate the system must have current knowledge about the human, technical, organizational, and environmental factors that determine the safety of the system as a whole, and have the tools and equipment available to perform their job duties in the safest manner possible. In addition, the organization must ensure that the personnel, procedures, and other resources needed to ensure safety are available. Understaffing safety-critical positions or not having formal, written procedures for ensuring safety can be just as detrimental as a lack of physical equipment.